## Sheet1
PROJECT TIMELINE
| MILESTONE LABEL | DATE
| Milestone 1 | 2018-10-01
| Milestone 2 | 2018-10-04
| Milestone 3 | 2018-10-07
| Milestone 4 | 2018-10-10
| Milestone 5 | 2018-10-11
| Project Start | 2018-10-01 |  | columns used to create the chart
CATEGORY | TASK | START | END
Setup Firebase | Create an empty project and add Firebase to project | 2018-10-01 | 2018-10-01
Designing and Implementing the UIs | Design Wireframes for Each Screens | 2018-10-01 | 2018-10-02
| Implement the Wirefram Desing in the app | 2018-10-02 | 2018-10-03
| Apply Chosen Color Scheme for the App | 2018-10-03 | 2018-10-03
| Test App and add and/or change whatever is needed | 2018-10-04 | 2018-10-04
Setup and Creating Methods and Pages Needed for the Mobile Version | Use umlet to plan and design the methods, variables, logic, & classes needed for the app version | 2018-10-04 | 2018-10-04
| Create and flesh out Methods that are linked to the buttons and transactions to the app based off the Umlet | 2018-10-05 | 2018-10-06
| Test App and add and/or change whatever is needed | 2018-10-06 | 2018-10-07
Setup and Creating Methods and Pages Needed for the Web Version | Design an Umlet for the code and logic of the web version | 2018-10-08 | 2018-10-08
| Apply code, logic, and design for the web version | 2018-10-08 | 2018-10-09
| Finish & test website and add and/or change whatever is needed | 2018-10-10 | 2018-10-10
Complete Integration of Each Version, Ready to Use | Complete inegration for both the app and website. Test app & website and make necessary changes | 2018-10-10 | 2018-10-11